## Renzo
To-do list
To be completed by: |  |  | Name: Renzo
Deadline: |  |  | Date 12.16. 2025
Project 1
% done | Phase | Start By | Due By | Number Of Days | Revision Notes
100% | Planning | 2025-12-10 | 2025-12-12 | 1 | Review project requirements and rubric
100% | Preparation | 2025-12-10 | 2025-12-13 | 1 | Define table structures and attributes based on schema requirements
100% | Task A | 2025-12-12 | 2025-12-14 | 2 | Assign primary keys and foreign keys to all tables
100% | Task B | 2025-12-13 | 2025-12-15 | 2 | Map UDTs to tables using ERD and provided PDF
100% | Task C | 2025-12-14 | 2025-12-16 | 1 | Validate table definitions against ERD and rubric
100% | Task d- Screen Sharing and Presentation walkthrough | 2025-12-15 | 2025-12-16 | 1 | Revise tables based on feedback from coding team
0% | Paperwork | 2025-12-16 | 2025-12-16 | 1 | Final table verification and group recoding before submission

## Bryan
To-do list
To be completed by: |  |  | Name: Bryan
Deadline: |  |  | Date 12.16. 2025
Project 1
% done | Phase | Start By | Due By | Number Of Days | Revision Notes
100% | Planning | 2025-12-10 | 2025-12-12 | 1 | Review ERD and table relationships
100% | Preparation | 2025-12-10 | 2025-12-13 | 1 | Draft initial ERD showing entities and relationships
100% | Task a | 2025-12-12 | 2025-12-14 | 2 | Incorporate UDT usage into diagram annotations
100% | Task b | 2025-12-13 | 2025-12-15 | 2 | Validate cardinalities and relationships
100% | Task c | 2025-12-14 | 2025-12-16 | 1 | Update diagrams based on table and coding feedback
100% | Task d- Screen Sharing and Presentation walkthrough | 2025-12-15 | 2025-12-16 | 1 | Finalize ERD for presentation and submission
0% | Paperwork | 2025-12-16 | 2025-12-16 | 1 | Upload to Brightspace + notify professor.

## Devak
To-do list
To be completed by: |  |  | Name: Devak
Deadline: |  |  | Date 12.16. 2025
Project 1
% done | Phase | Start By | Due By | Number Of Days | Revision Notes
100% | Planning | 2025-12-10 | 2025-12-12 | 1 | Review project requirements and rubric
100% | Preparation | 2025-12-10 | 2025-12-13 | 1 | Analyze database schema and identify all required UDTs
100% | Task a | 2025-12-12 | 2025-12-14 | 2 | Define UDT purposes, constraints, and defaults
100% | Task b | 2025-12-13 | 2025-12-15 | 2 | Map UDTs to tables using ERD and provided PDF
100% | Task c | 2025-12-14 | 2025-12-16 | 1 | Draft UDT explanation slides with examples
100% | Task d- Screen Sharing and Presentation walkthrough | 2025-12-15 | 2025-12-16 | 1 | Tested Zoom Meetings but run into issues, so opted to Google Meetings, Running queries real-time by multitasking between DBeaver & Jupyter Notebook
0% | Paperwork | 2025-12-16 | 2025-12-16 | 1 | Upload to Brightspace + notify professor.

## Nadia
To-do list
To be completed by: |  |  | Name: Nadia
Deadline: |  |  | Date 12.16. 2025
Project 1
% done | Phase | Start By | Due By | Number Of Days | Revision Notes
100% | Planning | 2025-12-10 | 2025-12-12 | 1 | Created and recreated the ClassSchedule database
100% | Preparation | 2025-12-10 | 2025-12-13 | 1 | Defined all schemas (Uploadfile, Faculty, CollegeCatalog, Campus, ClassSession, DbSecurity, Process)
100% | Task a | 2025-12-12 | 2025-12-14 | 2 | Implemented all base and core tables
100% | Task b | 2025-12-13 | 2025-12-15 | 2 | Applied primary keys, foreign keys, unique constraints, and defaults
100% | Task c | 2025-12-14 | 2025-12-16 | 1 | Ensured referential integrity across all base entities
100% | Task d- Screen Sharing and Presentation walkthrough | 2025-12-15 | 2025-12-16 | 1 | Recorded with my team members.
0% | Paperwork | 2025-12-16 | 2025-12-16 | 1 | Upload to Brightspace + notify professor.

## Htoo
To-do list
To be completed by: |  |  | Name: Htoo
Deadline: |  |  | Date 12.16. 2025
Project 1
% done | Phase | Start By | Due By | Number Of Days | Revision Notes
100% | Planning | 2025-12-10 | 2025-12-12 | 1 | Implemented workflow and utility stored procedures,
100% | Preparation | 2025-12-10 | 2025-12-13 | 1 | Created lookup and parent-table loaders,
100% | Task a | 2025-12-12 | 2025-12-14 | 2 | Ensured all procedures properly stamped UserAuthorizationKey
100% | Task b | 2025-12-13 | 2025-12-15 | 2 | Integrated workflow auditing into each loader
100% | Task c- Screen Sharing and Presentation walkthrough | 2025-12-15 | 2025-12-16 | 1 | Recorded with my team members.
0% | Paperwork | 2025-12-16 | 2025-12-16 | 1 | Upload to Brightspace + notify professor.

## Alexander
To-do list
To be completed by: |  |  | Name: Alexander
Deadline: |  |  | Date 12.16. 2025
Project 1
% done | Phase | Start By | Due By | Number Of Days | Revision Notes
100% | Planning | 2025-12-10 | 2025-12-12 | 1 | Implemented core entity loader stored procedures
100% | Preparation | 2025-12-10 | 2025-12-13 | 1 | Developed the master loader procedure to orchestrate the full ETL process
100% | Task a | 2025-12-12 | 2025-12-14 | 2 | Managed execution order, error handling, and workflow logging
100% | Task b | 2025-12-13 | 2025-12-15 | 2 | Ensured foreign keys were safely dropped and re-enabled during loads
100% | Task c- Screen Sharing and Presentation walkthrough | 2025-12-15 | 2025-12-16 | 1 | Recorded with my team members.
0% | Paperwork | 2025-12-16 | 2025-12-16 | 1 | Upload to Brightspace + notify professor.