## Group member 1
To-do list
To be completed by: |  |  |  | Name Devak Mehta
Deadline: |  |  |  | Date October 17 2025
Project 4
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2025-10-15 | 2025-10-15 | 2025-10-16 | 1 | Outlined group plan. Due to Andrea being removed last second, came up with restructure plan of 2-2-1
75% | Preparation | 2025-10-15 | 2025-10-16 | 2025-10-16 | 2 | Set up the new Sql setup with createengine() and run()
50% | Task A – Chapter 6 Queries | 2025-10-16 | 2025-10-16 | 2025-10-16 | 2 | Created and debugged set operations queries.
25% | Task B – Chapter 6 Queries revision | 2025-10-17 | 2025-10-17 | 2025-10-17 | 1 | Made sure the new sql connection was stable, recorded individiual video
0% | Task C – Markdown Explanations | 2025-10-17 | 2025-10-17 | 2025-10-17 | 2 | Add business rationale + NACE Competency links.
0% | Paperwork | 2025-10-17 | 2025-10-17 | 2025-10-17 | 1 | Ensure Renzo adds video URL and GitHub repo link.
0% | Hand-off | 2025-10-17 | 2025-10-17 | 2025-10-17 | 1 | Upload to Brightspace + notify professor.

## Group member 2
To-do list
To be completed by: |  |  |  | Renzo (Leader)
Deadline: |  |  |  | 2025-10-17
Project 3
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2025-10-14 | 2025-10-15 | 2025-10-15 | 1 | Assigned roles & confirmed scope with professor.
75% | Preparation | 2025-10-15 | 2025-10-15 | 2025-10-15 | 1 | Created shared folder + SQL schema references.
50% | Task A – SQL Query Integration | 2025-10-15 | 2025-10-15 | 2025-10-16 | 3 | Added queries and went over the order of presentation
25% | Task B – Script and Narration | 2025-10-16 | 2025-10-16 | 2025-10-16 | 2 | Drafted video script for presentation.
0% | Task C – Video Recording | 2025-10-16 | 2025-10-16 | 2025-10-16 | 1 | Set up OBS recording with David. The teams were switched up last minute so we decided to do 2-1-1 structure. Devak took the responsibilty to do it alone
0% | Paperwork | 2025-10-16 | 2025-10-16 | 2025-10-16 | 1 | Edit video confirm uploads and check on my teammayes
0% | Hand-off | 2025-10-17 | 2025-10-17 | 2025-10-17 | 1 | Submit final files on Brightspace.

## Group member 3
To-do list
To be completed by: |  |  |  | David
Deadline: |  |  |  | 2025-10-17
Project 4
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2025-10-14 | 2025-10-15 | 2025-10-15 | 1 | Reviewed assignment instructions.
75% | Preparation | 2025-10-14 | 2025-10-15 | 2025-10-15 | 1 | Set up Dbeaver connection
50% | Task A – Query Testing | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2 | Ran queries with different IDs and logged outputs.
25% | Task b- Screenshots | 2025-10-15 | 2025-10-16 | 2025-10-16 | 1 | Captured code + result screens for report.
0% | Task C – Data Formatting | 2025-10-16 | 2025-10-17 | 2025-10-16 | 1 | Aligned column headings and output display.
0% | Paperwork | 2025-10-16 | 2025-10-16 | 2025-10-17 | 1 | Check file names per Brightspace rules.
0% | Hand-off | 2025-10-16 | 2025-10-16 | 2025-10-17 | 1 | Upload folder to shared drive.

## Group member 4
To-do list
To be completed by: |  |  |  | Bryan
Deadline: |  |  |  | 2025-10-17
Project 4
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2025-10-14 | 2025-10-15 | 2025-10-15 | 1 | planned with Ajay to see whats our common avalabilities
75% | Preparation | 2025-10-14 | 2025-10-15 | 2025-10-15 | 1 | Set up sql connection server
50% | Task A – Query Testing | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2 | worked on queries for hw6 using SET operators
25% | Task b- Cross-checking | 2025-10-15 | 2025-10-16 | 2025-10-16 | 1 | crosschecked queries
0% | Task C – Video recording | 2025-10-16 | 2025-10-17 | 2025-10-16 | 1 | Recorded my video with Ajay.
0% | Paperwork | 2025-10-16 | 2025-10-16 | 2025-10-17 | 1 | Check file names per Brightspace rules.
0% | Hand-off | 2025-10-16 | 2025-10-16 | 2025-10-17 | 1 | Upload folder to shared drive.

## Group member 5
To-do list
To be completed by: |  |  |  | Ajay
Deadline: |  |  |  | 2025-10-17
Project 4
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2025-10-14 | 2025-10-15 | 2025-10-15 | 1 | Discussed with the group about how to approach the hw
75% | Preparation | 2025-10-14 | 2025-10-15 | 2025-10-15 | 1 | Connected to the new database
50% | Task A – Query Formulation | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2 | Formulated queries after meeting with bryan and talking with the team
25% | Task b- propositions | 2025-10-15 | 2025-10-16 | 2025-10-16 | 1 | made proper propositions for the queries with working
0% | Task C – Video recording | 2025-10-16 | 2025-10-17 | 2025-10-16 | 1 | Recorded my video with Bryan.
0% | Paperwork | 2025-10-16 | 2025-10-16 | 2025-10-17 | 1 | Check file names per Brightspace rules.
0% | Hand-off | 2025-10-16 | 2025-10-16 | 2025-10-17 | 1 | Upload folder to shared drive.