## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Group member 1
| Table 1 | Group member 1
Group member 2
| Table 1 | Group member 2
Group member 3
| Table 1 | Group member 3

## Group member 1
To-do list
To be completed by: |  |  |  | Name Devak Mehta
Deadline: |  |  |  | Date October 17 2025
Project 3
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2025-10-06 | 2025-10-07 | 2025-10-07 | 1 | Outlined group plan, divided 30 queries (10 each).
75% | Preparation | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2 | Set up DB connection (mssql+pyodbc) & tested DBeaver.
50% | Task A – Chapter 4 Queries | 2025-10-08 | 2025-10-09 | 2025-10-09 | 2 | Created and debugged multi-table WHERE/GROUP BY queries.
25% | Task B – Chapter 5 Queries | 2025-10-09 | 2025-10-09 | 2025-10-09 | 1 | Worked on DECLARE variables and subqueries in Jupyter.
0% | Task C – Markdown Explanations | 2025-10-09 | 2025-10-09 | 2025-10-10 | 2 | Add business rationale + NACE Competency links.
0% | Paperwork | 2025-10-10 | 2025-10-10 | 2025-10-10 | 1 | Ensure Renzo adds video URL and GitHub repo link.
0% | Hand-off | 2025-10-10 | 2025-10-10 | 2025-10-10 | 1 | Upload to Brightspace + notify professor.

## Group member 2
To-do list
To be completed by: |  |  |  | Renzo (Leader)
Deadline: |  |  |  | 2025-10-17
Project 3
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2025-10-05 | 2025-10-05 | 2025-10-06 | 1 | Assigned roles & confirmed scope with professor.
75% | Preparation | 2025-10-06 | 2025-10-06 | 2025-10-06 | 1 | Created shared folder + SQL schema references.
50% | Task A – SQL Query Integration | 2025-10-06 | 2025-10-09 | 2025-10-09 | 3 | Added queries and went over the order of presentation
25% | Task B – Script and Narration | 2025-10-08 | 2025-10-09 | 2025-10-09 | 2 | Drafted video script for presentation.
0% | Task C – Video Recording | 2025-10-10 | 2025-10-10 | 2025-10-10 | 1 | Set up OBS recording with Devak and David. The teams were switched up last minute so we decided to do us three togteher since we had no contact with old teammates
0% | Paperwork | 2025-10-10 | 2025-10-10 | 2025-10-10 | 1 | Edit video confirm uploads and check on my teammayes
0% | Hand-off | 2025-10-10 | 2025-10-10 | 2025-10-10 | 1 | Submit final files on Brightspace.

## Group member 3
To-do list
To be completed by: |  |  |  | David
Deadline: |  |  |  | 2025-10-17
Project 3
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2025-10-05 | 2025-10-06 | 2025-10-06 | 1 | Reviewed assignment instructions.
75% | Preparation | 2025-10-05 | 2025-10-06 | 2025-10-06 | 1 | Set up Dbeaver connection
50% | Task A – Query Testing | 2025-10-06 | 2025-10-08 | 2025-10-08 | 2 | Ran queries with different IDs and logged outputs.
25% | Task b- Screenshots | 2025-10-08 | 2025-10-09 | 2025-10-09 | 1 | Captured code + result screens for report.
0% | Task C – Data Formatting | 2025-10-09 | 2025-10-10 | 2025-10-10 | 1 | Aligned column headings and output display.
0% | Paperwork | 2025-10-10 | 2025-10-10 | 2025-10-10 | 1 | Check file names per Brightspace rules.
0% | Hand-off | 2025-10-10 | 2025-10-10 | 2025-10-10 | 1 | Upload folder to shared drive.